## Sheet1
The Master's Thesis has 24 credits, which is equivalent to a studyload of 600-720 hours. If you spread that over the instruction weeks, this means a weekly average of 40-50 hours per week
| date | Week | TODO | DONE | TODO Cum | DONE Cum | notes
| 2022-07-11 | 28 | 15 | 22 | 15 | 22 | reading
| 2022-07-18 | 29 | 15 | 15 | 30 | 37 | reading
| 2022-07-25 | 30 | 20 | 26 | 50 | 63 | reading
| 2022-08-01 | 31 | 20 | 20 | 70 | 83 | writing
| 2022-08-08 | 32 | 20 | 26 | 90 | 109 | writing, proofreading
| 2022-08-15 | 33 | 15 | 6 | 105 | 115 | kickoff
| 2022-08-22 | 34 | 0 | 0 | 105 | 115 | examen
| 2022-08-29 | 35 | 25 | 25 | 130 | 140 | reading
| 2022-09-05 | 36 | 30 | 34 | 160 | 174 | reading
| 2022-09-12 | 37 | 25 | 26 | 185 | 200 | writing
| 2022-09-19 | 38 | 30 | 35 | 215 | 235 | proofreading
| 2022-09-26 | 39 | 40 | 43 | 255 | 278 | coding a fuzzer
| 2022-10-03 | 40 | 40 | 33 | 295 | 311 | Modifying Storm
| 2022-10-10 | 41 | 16 | 19 | 311 | 330 | Modifying Storm
| 2022-10-17 | 42 | 16 | 37 | 327 | 367 | Modifying Storm
| 2022-10-24 | 43 | 40 | 44 | 367 | 411 | Diff testing, Metamorphic testing
| 2022-10-31 | 44 | 35 | 39 | 402 | 450 | Metamorphic testing
| 2022-11-07 | 45 | 35 | 39 | 437 | 489 | running tests, reproducing bugs
| 2022-11-14 | 46 | 35 | 24 | 472 | 513 | Result processing
| 2022-11-21 | 47 | 35 | 0 | 507 | 513 | Result processing
| 2022-11-28 | 48 | 35 | 0 | 542 | 513 | Result processing
| 2022-12-05 | 49 | 35 | 0 | 577 | 513 | writing
| 2022-12-12 | 50 | 35 | 0 | 612 | 513 | writing
| 2022-12-19 | 51 | 35 | 0 | 647 | 513 | writing + asking permission
| 2022-12-26 | 52 | 35 | 0 | 682 | 513 | writing
| 2023-01-02 | 1 | 20 | 0 | 702 | 513 | Proofreading
| 2023-01-09 | 2 | 20 | 0 | 722 | 513 | proofreading + submitting
| 2023-01-16 | 2 | 0
cum |  |  | 722 | 513
buffer | 41
235
Formulas:
date = [date, row above]+7

## Sheet2
date | Week | uren | maandag | dinsdag | woensdag | donderdag | vrijdag | zaterdag | zondag
2022-07-11 | 28 | 22 | fac, CW, DTAI guidelines gelezen, lextex template klaar gezet, timesheet gemaakt | starting paper gelezen, korte brain storming over inleidende hoofdsctuk, terminologie opgezocht, back-up methodes opgezegt voor de paper | reading paper "Fuzzing and delta-debugging SMT solvers.", reading documantations on fuzzer afl(++), finding some books on limo | paper 2,3, chapter 5 Simplifying Problems 2009 Why Programs Fail | chapter 13 Simplifying Problems 2009 Why Programs Fail, reading 5 delta-debugging Simplifying and Isolating Failure-Inducing Input till p9, trying to understand the algoritms | cont 5 reading Simplifying and Isolating Failure-Inducing Input, reading for fuzzing 6 Language Fuzzing Using Constraint Logic Programming, 7 Parser-Directed Fuzzing | reading 8 KLEE Unassisted and Automatic Generation of High-Coverage, rereading starting paper, 9 Automatically Testing String Solvers.pdf until page 4
2022-07-18 | 29 | 15 | 36°C | 38°C | reading 9 Automatically Testing String Solvers, reading 10 The Oracle Problem in Software | Trying out CPMpy, reading documentation of CPMpy | watching "CP2021 Tutorial "CPMpy, a Numpy-based CP Modeling Environment", trying out CPMpy further, reading 11 Freuder1997_Article_InPursuitOfTheHolyGrail | tutorial_ijcai22 pdf's, reading 12 Fuzzing a survey | reading 13 The Art, Science, and Engineering, reading 14 Optimizing Seed Selection for Fuzzing
2022-07-25 | 30 | 26 | reading 15 Ganesh-2009-Taint-based directed whitebox fuzzing, reading 16 Fuzzing for Software Security Testing and Quality Assurance, reading Increasing modeling language convenience with a universal n-dimensional array, CPpy as python-embedded example | reading 17 CPMpy paper modref19_cppy, reading 18 Model-Based Algorithm ConfigurationCPAIOR22_DeCaprio, reading 19 Numberjack, reading some parts of 20 Constraint Solving and Planning with picat | writing intro, dividing chapters | Writing chapter 1 intro and genretation vs mutation, fixing sources, getting to know the editor better | writing about input generation techniques | writing about sat by construction, oracel start, classification of bugs | start writing about types of fuzzer, finding more Miller papers, reading 22 Semantic Fuzzing with Zest, reading 23 Theoretical and Empirical Studies of Program Testing
2022-08-01 | 31 | 20 | writing about multiple available fuzzers, reading 26 fuzz revisited: A Re-examinationn of the reliaility of UNIX utilities and services, first proof reading of the parts already written | Checking out the changes on the CPMpy github | reading 28 Understanding the Blockchain Oracle Problem, half reading 29 Programs, Tests, and Oracles, writing about oracles diff testing and a bit of intro. | reading multiple blogs about finding CVE's with fuzzing, reading about popular exploits, writing fuzzing in development and fuzzing in security | Hobby Stura | reading 32 V-Fuzz: Vulnerability-Oriented Evolutionary Fuzzing, reading 33 Release the Kraken: New KRACKs in the 802.11 Standard, reading 34 DIFUZZRTL Differential Fuzz Testing to Find, partial reading 35Microarchitectural Side-Channel Attacks for Privileged Software Adversaries, wmall writing part | Finishing of chapter 2
2022-08-08 | 32 | 26 | written example of debugging in intro, written intro ch3, written start of deduplication, read 36 RETracer from Microsoft | Writing start of simplification of inputs, reading 38 Data_deduplication_techniques | writing Deobfuscating inputs, structuring chapter 3 and 4, cleaning out bib | writing The precision effect, rewording What size to change | almost finishing chapter 3, structuring chapter 4, adding labels, rereading some papers | proofreading chap2, reading 27 AFL++: Combining Incremental Steps of Fuzzing Research | proofreading ch 2 futher, proofreading ch 3, found new section for ch 2
2022-08-15 | 33 | 6 | prep kickoff, trying AFL on CPMpy, debugging AFL, failing | Kick-off masterproef, finding book | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems
2022-08-22 | 34 | 0 | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems | Self adaptive Systems
2022-08-29 | 35 | 25 | Self adaptive Systems | Self adaptive Systems | Reading 40 SolverCheck: Declarative Testing of Constraints, Reading 41 Grammar-based Whitebox Fuzzing, finding fuzzing with SMT-papers, reading 42 Fuzzing SMT Solvers via Two-Dimensional, Reading 43 Validating SMT Solvers via Semantic Fusion | Rereading FuzzSMT Fuzzing and Delta-Debugging SMT Solver, Rereading strom Detecting Critical Bugs in SMT Solvers Using Blackbox Mutational Fuzzing, Reading 44 StringFuzz: A Fuzzer for String Solvers, Rereading 8 KLEE Unassisted and Automatic Generation of High-Coverage, Reading 45 fuzzball Path-Exploration Lifting Hi-Fi Tests for Lo-Fi Emulators, Reading 47 Finding and Understanding Bugs in Software Model Checkers, Reading 48 Differentially Testing Soundness and Precision of Program Analyzers | thesis meeting, perperation work | Reading on minimal unsatisfiable subset, Reading 49 TestMC Testing Model Counters using Differential and Metamorphic Testing, Reading 50 Metamorphic testing of constraint solvers, adding parts to further write on | Writing SMT fuzzers, expanding previous parts
2022-09-05 | 36 | 34 | Writing on SMT, CP fuzzers like Falcon, Writing on Metamorphic testing, Finishing of multople To Do's | Hobby Stura | Writing connection between MUS/MSS Simplification/Isolation, Reading 51 Algorithms for Computing Minimal Unsatisfiable Subsets of Constraints | Writing about deobfuscation algoritmes struglling with LaTeX, Reading 52 Constraint Programming In Pursuit of the Holy Grail | thesis meeting, Reading 53 some chapters of Programming with Constraints An Introduction, Reading 54 Z3 978-3-540-78800-3_24, Reading 56 Bringing CP, SAT and SMT together Next Challenges in Constraint Solving dagrep_v009_i002_p027_19062.pdf, Reading 57 MiniZinc Towards a Standard CP Modelling Language 978-3-540-74970-7-543-557.pdf, more explanation on an example, Reading 58 The Minizinc challenge 2008-2013 2539-Article Text-4467-1-10-20140610.pdf | Reading partial On Induction for SMT Solvers main-tech-report, Reading 59 Philosophy of the MINIZINC challenge s10601-010-9093-020160730-1147-1vmoz0t-with-cover-page-v2, Reading 60 Empirical Study of the Anatomy of Modern SAT Solvers, Rereading parts of Modelling of Complex Systems - Courese Text, finding papers | Reading to find gaps in knowledge Wiki's: Constraint_logic_programming, Constraint_programming, Constraint_satisfaction_problem, DPLL(T), Operations_research, Quantifier_(logic), Satisfiability_modulo_theories, Z3_Theorem_Prover
2022-09-12 | 37 | 26 | Writing start of CP chapter, Writing explaining "send + more = money" example, fighting LaTeX while using a listing style for Minizinc, some quality of life improvements in LaTeX | Writing around CP sat and optimalisations,Writing around minizinc and its challenges, Reading 65 Constraint Logic Programming, Reading 67 Lazy Clause Generation Combining the power of SAT and CP (and MIP) solving, Reading 68 The Modelling Language Zinc 10.1.1.111.5598, Reading 69 Compiling Finite Domain Constraints to SAT with BEE 1206.3883 | Writing about MiniZinc Challenge and CPMpy, Reading 70 Essence A Constraint Language for Specifying Combinatorial Problems essence | Writing about SAT, SMT, Reading 71 CVC3, Reading 72 A System for Solving Constraint Satisfaction Problems with SMT bofill-sat10.pdf | korte reis | korte reis | korte reis
2022-09-19 | 38 | 35 | kot verhuis | Writing conclusion of chapter CP, proofreading chapter CP, partial reading 73 Simplify A Theorem Prover for Program Checking 1066100.1066102.pdf | Proofreading chapter CP, adding conclusion to chapter deofuscation, adding to intro chapter, proofreading intro chapter and chapter around fuzzing, fighting Biber | Proofreading the end of fuzzing, proofreading critical part chapter, rereading parts of papers, stdizing quotes | Proofreading via Word, schrijfhulp and other tools | Finding research Questions, brainstorming in general | More research Questions
2022-09-26 | 39 | 43 | Thesis meeting, processing meeting notes | Playing around with Storm, reading Storm's source code, converting ipynb to py | Getting Minizinc, gurobi and pysat to work on W10 (dev/debug env) and linux (execute env), running some tests | Writing a transformation fucntion to change the seed solver to Minizinc | trying out LaTeX packages, Improving solver transformation (fixing MissingAttributeErrores), speed testing | Running more test, evaluation results, Reading DTAI's site | DataProcessing
2022-10-03 | 40 | 33 | prep + Thesis meeting, processing meeting notes, installing extra imports, writing a program to export Pickles | Exporting Pickles (seeds files), Reading STOM's code base, trying to get STORM to work | Rewriting STORM to fit CPMpy | recreating seeds, finding out how to evaluate subformulas thanks to Mr Bleukx | Finding the DTAI Toledo community, planning, watching Milestone M1
2022-10-10 | 41 | 19 | thesis meeting, finishing off STORM convertion, starting debugging new storm | Debugging new STORM, investigating why cpmpy does not set model.status() when using solverlookup()+ seminar | Finding ~(alldifferent()-bug) | Operatie | Revalidatie | Revalidatie | Revalidatie
2022-10-17 | 42 | 37 | Revalidatie, solving ~ Global function bug, writing a around chapter 5 Research Questions | Writing and bug exploration + seminar | solving env variables problems, running the big fuzzer on a server, writing a small minimizer (I use musx given by CPMpy <3) | debugging error that occurs after x hours, output investigation | requesting thesis in English, fixing yet another bug in big run, adding timeout to deobfucation, brainstorm about next technique, workshop thesis: Information Literacy |  | looking at results
2022-10-24 | 43 | 44 | preping results for thesis meeting, thesis meeting, bug reporting, looking at ways to get stacktraces, Improving the modified Storm Thanks to Ignace's tips | Mostly making presentation for M2 (rough day) | building differential testing, debugging some errors (thanks to Linux for OOM killer) | Finishing ppt, learining ppt, looking at recent CPMpy changes, debugging diff tester, writing patch for diff tester | debugging OOM Killer bug, rerunning tests, writing a bit | updating notes, Rereading papers about meta and diff testing
2022-10-31 | 44 | 39 | starting coding at metaporphic testing, finding out which functions are available, implementing some metaporphic relations | feestdag, brainstorm about metamorphic relations, implementing some | coding more meta relations, debugging meta relations, restarting crashed diff, restarting STROM, filtering seed files that cause crashes | Practicing presentation, updating planning, extending diff testing to solve() instead of solveAll() only, setting error filter for diff testing | Prepping presentation, presentation, looking at the first outputs of diffv1, running diffv2, changing some diff filters | writing about diff testing, getting some values to put in text, prepping thesis meeting
2022-11-07 | 45 | 39 | prepping thesis meeting, thesis meeting by mail, filtering out pickles that slipped into the seeds, modif diff, running meta, reproducing bugs | reproducing bugs, trying to install minizing:ortools, seminar | reproducing bugs, writing own MUS (both in simplification and isolation techniques), installing minizinc:ortools op w10 (jezus wat een miserie) | installing minizinc:ortools on ubuntu (yikes the install errors), reproducing bugs, rerunning with new solver | reproducing bugs, writing about metamorphic testing | submitting some more obvious bugs | creating excel for labeling bugs
2022-11-14 | 46 | 24 | prepping thesis meeting, thesis meeting by mail, submitting + labeling bugs, running fuzzers, reproducing/minimizing newlly found bugs | finishing reproducing diff bugs, reporting new ones | Reproducing meta crashes, Reproducing STORM random errors and crashes, building tools to auto reproduces STORM's soundsness bugs
2022-11-21 | 47 | 0
2022-11-28 | 48 | 0
2022-12-05 | 49 | 0
2022-12-12 | 50 | 0 |  |  |  | ASK PERMISSION
2022-12-19 | 51 | 0 | ASK PERMISSION
2022-12-26 | 52 | 0
2023-01-02 | 1 | 0
2023-01-09 | 2 | 0 |  |  |  | SUBMISSION DAY | ################################### | ################################### | ###################################
2023-01-16 | 3 | 0 | ################################### | ################################### | ################################### | ################################### | ################################### | ################################### | ###################################
|  |  | Turn on Excuses: | TRUE
Formulas:
date = [date, row above]+7